## Sheet1
[8 empty] | Format 1 | Format 2
| 1 | Inputs | Doctor | Patient | Dealer | Legal | Law of Country | Attach scanned docs | Text Input/Top Management Inputs/Discussions
|  | 11 | 22 | 33 | 44 | 55 | 66
| 2 | Give Each Input a Unique ID | Doctor | Patient | Dealer | Legal | Law of Country | Format 1 | Format 2 | RECORD THE DECISION
[8 empty] | Attach scanned docs | Text Input/Top Management Inputs/Discussions | Review Team Signature | Review Team Comments | Accept /Reject
| 3 | Discussion on Each Input | Doctor | Patient | Dealer | Legal | Law of Country | Format 1 | Format 2 | RECORD THE DECISION
|  | ACCEPT OR REJECT | [5 empty] | Attach scanned docs | Text Input/Top Management Inputs/Discussions | Review Team Signature | Review Team Comments | Accept /Reject
TRACEABILITY NEEDED FOR EACH ID
ASSIGN TH E TEAM AND THEIR RESPONSIBILITIES
DEVELOPMENT WORK STARTS
|  | Make a Regulatory Pathway | New Document
Activities
|  | 4 | Create Documents | Drawings | Specifications | Test Methods | Testing | Format 1 | Format 2 | RECORD THE DECISION |  |  | Decide how you will get the data and then someone has to review and approve it
[8 empty] | Attach scanned docs | Text Input/Top Management Inputs/Discussions | Review Team Signature | Review Team Comments | Accept /Reject
|  | 4a | Procure Material for new product development | Create Vendor List | Place Purchase Order | Track Purchase Order with its status | Track Material receipt
|  | 4b | Make the product | Stepwise pictures will be taken, test data generate, external testing |  |  |  | Format 1 | Format 2 | RECORD THE DECISION |  |  | Decide how you will get the data and then someone has to review and approve it
[8 empty] | Attach scanned docs | Text Input/Top Management Inputs/Discussions | Review Team Signature | Review Team Comments | Accept /Reject
Change Management
|  | 5 | Compare your 4b output against each input from 3 | Discussion | Picture | Lab Report | Customer Feedback | Format 1 | Format 2 | RECORD THE DECISION |  |  | Track any change made | Tack any inputs at any stage | Review and approval of change
|  |  | THIS IS MY FIRST SUCCESS WITH THE PRODUCT |  |  |  |  | Attach scanned docs | Text Input/Top Management Inputs/Discussions | Review Team Signature | Review Team Comments | Accept /Reject
|  | 6 | Repeat your experiment 3 times | Discussion | Picture | Lab Report | Process Parameters | Format 1 | Format 2 | RECORD THE DECISION |  |  | Change Management
|  |  | Compare your 5 output against 6 | NOW I WANT TO BE SURE ABOUT THE PROCESS |  |  |  | Attach scanned docs | Text Input/Top Management Inputs/Discussions | Review Team Signature | Review Team Comments | Accept /Reject | Track any change made | Tack any inputs at any stage | Review and approval of change
|  | 7 | Final Vendor Data | Final Process Data | Final Packing data | Final IFU | Final Documents for the product | Format 1 | Format 2 | RECORD THE DECISION |  |  | Change Management
[8 empty] | Attach scanned docs | Text Input/Top Management Inputs/Discussions | Review Team Signature | Review Team Comments | Accept /Reject | Track any change made | Tack any inputs at any stage | Review and approval of change
|  | 7a | Repeat your experiment 3 times in actual environment | Discussion | Picture | Lab Report | Process Parameters
|  |  | Compare your 7a output against 7 | NOW I WANT TO BE SURE ABOUT THE SCALABILITY |  |  |  | Format 1 | Format 2 | RECORD THE DECISION |  |  | Change Management
[8 empty] | Attach scanned docs | Text Input/Top Management Inputs/Discussions | Review Team Signature | Review Team Comments | Accept /Reject | Track any change made | Tack any inputs at any stage | Review and approval of change
FINAL OUTPUT
FINAL OUTPUT |  | Design History File | Data is important for the R&D Team
|  | Design Transfer File | Data is important for the Production and Regulatory Team

## Sheet2
specs
BULB | ID/OD/
DISPLAY | 3mmx2mm
WIRE | 4cm
SENSOR | philips x
BODY | triveni drawing no 334
CREATING THE PRODUCT |  | VERIFICATION | VALIDATION
EXPERIMENT | 1 CUP TEA |  | 1 CUP TEA | 1 CUP TEA | 1 CUP TEA | 1 CUP TEA | 1 CUP TEA | 1 CUP TEA
TEA LEAVES | 10g |  | 10g | 10g | 10g | 10g | 10g | 10g
WATER | 100ml |  | 125ml | 125ml | 125ml | 125ml | 125ml | 125ml
SUGAR | 1 SPOON |  | 2SPOON | 2SPOON | 2SPOON | 2SPOON | 2SPOON | 2SPOON
CUP | 1 |  | 1 | 1 | 1 | 1 | 1 | 1
SAUCER | 1 |  | 1 | 1 | 1 | 1 | 1 | 1
BOILING TEMP | 85 degree |  | 100degree | 100degree | 100degree | 100degree | 100degree | 100degree
BOILING TIME | 5MIn |  | 10MIN | 10MIN | 10MIN | 10MIN | 10MIN | 10MIN
REVIEW | REJECT |  | ACCEPT | ACCEPT | ACCEPT | ACCEPT | ACCEPT | ACCEPT
[7 empty] | 1 CUP TEA | 1 CUP TEA
[7 empty] | 10g | 10g
TRANSFER | [6 empty] | 125ml | 125ml
PRODUCTION | [6 empty] | 2SPOON | 2SPOON
[7 empty] | 1 | 1
[7 empty] | 1 | 1
[7 empty] | 100degree | 100degree
[7 empty] | 10MIN | 10MIN
[7 empty] | ACCEPT | ACCEPT

## Sheet3
7.3 Design and development..............................................................................................................................................................14
7.3.1 General...................................................................................................................................................................................14
7.3.2 Design and development planning.................................................................................................................14
7.3.3 Design and development inputs.......................................................................................................................14
7.3.4 Design and development outputs...................................................................................................................15
7.3.5 Design and development review......................................................................................................................15
7.3.6 Design and development verification..........................................................................................................15
7.3.7 Design and development validation..............................................................................................................15
7.3.8 Design and development transfer...................................................................................................................16
7.3.9 Control of design and development changes.........................................................................................16
7.3.10 Design and development files.............................................................................................................................16
7.3 Design and development | 1 |  | PICTURE
7.3.1 General
The organization shall document procedures for design and development.
7.3.2 Design and development planning
The organization shall plan and control the design and development of product. As appropriate, design and development planning documents shall be maintained and updated as the design and development progresses.
During design and development planning, the organization shall document: | 2 | Articles and Research Papers | PDF FORMAT/PIC
a) the design and development stages;
b) the review(s) needed at each design and development stage;
c) the verification, validation, and design transfer activities that are appropriate at each design and development stage;
d) the responsibilities and authorities for design and development;
e) the methods to ensure traceability of design and development outputs to design and development inputs;
f) the resources needed, including necessary competence of personnel.
7.3.3 Design and development inputs
Inputs relating to product requirements shall be determined and records maintained (see 4.2.5). These inputs shall include:
a) functional, performance, usability and safety requirements, according to the intended use;
b) applicable regulatory requirements and standards;
c) applicable output(s) of risk management;
d) as appropriate, information derived from previous similar designs;
e) other requirements essential for design and development of the product and processes.
These inputs shall be reviewed for adequacy and approved.
Requirements shall be complete, unambiguous, able to be verified or validated, and not in conflict with each other.
NOTE Further information can be found in IEC 62366–1.
7.3.4 Design and development outputs
Design and development outputs shall:
a) meet the input requirements for design and development;
b) provide appropriate information for purchasing, production and service provision;
c) contain or reference product acceptance criteria;
d) specify the characteristics of the product that are essential for its safe and proper use.
The outputs of design and development shall be in a form suitable for verification against the design and development inputs and shall be approved prior to release.
Records of the design and development outputs shall be maintained (see 4.2.5).
7.3.5 Design and development review
At suitable stages, systematic reviews of design and development shall be performed in accordance with planned and documented arrangements to:
a) evaluate the ability of the results of design and development to meet requirements;
b) identify and propose necessary actions.
Participants in such reviews shall include representatives of functions concerned with the design and development stage being reviewed, as well as other specialist personnel.
Records of the results of the reviews and any necessary actions shall be maintained and include the identification of the design under review, the participants involved and the date of the review (see 4.2.5).
7.3.6 Design and development verification
Design and development verification shall be performed in accordance with planned and documented arrangements to ensure that the design and development outputs have met the design and development input requirements.
The organization shall document verification plans that include methods, acceptance criteria and, as appropriate, statistical techniques with rationale for sample size.
If the intended use requires that the medical device be connected to, or have an interface with, other medical device(s), verification shall include confirmation that the design outputs meet design inputs when so connected or interfaced.
Records of the results and conclusions of the verification and necessary actions shall be maintained (see 4.2.4 and 4.2.5).
7.3.7 Design and development validation
Design and development validation shall be performed in accordance with planned and documented arrangements to ensure that the resulting product is capable of meeting the requirements for the specified application or intended use.
The organization shall document validation plans that include methods, acceptance criteria and, as appropriate, statistical techniques with rationale for sample size.
Design validation shall be conducted on representative product. Representative product includes initial production units, batches or their equivalents. The rationale for the choice of product used for validation shall be recorded (see 4.2.5).
As part of design and development validation, the organization shall perform clinical evaluations or performance evaluations of the medical device in accordance with applicable regulatory requirements. A medical device used for clinical evaluation or performance evaluation is not considered to be released for use to the customer.
If the intended use requires that the medical device be connected to, or have an interface with, other medical device(s), validation shall include confirmation that the requirements for the specified application or intended use have been met when so connected or interfaced.
Validation shall be completed prior to release for use of the product to the customer.
Records of the results and conclusion of validation and necessary actions shall be maintained (see 4.2.4 and 4.2.5).
7.3.8 Design and development transfer
The organization shall document procedures for transfer of design and development outputs to manufacturing. These procedures shall ensure that design and development outputs are verified as suitable for manufacturing before becoming final production specifications and that production capability can meet product requirements.
Results and conclusions of the transfer shall be recorded (see 4.2.5).
7.3.9 Control of design and development changes
The organization shall document procedures to control design and development changes. The organization shall determine the significance of the change to function, performance, usability, safety and applicable regulatory requirements for the medical device and its intended use.
Design and development changes shall be identified. Before implementation, the changes shall be: a) reviewed;
b) verified;
c) validated, as appropriate;
d) approved.
The review of design and development changes shall include evaluation of the effect of the changes on constituent parts and product in process or already delivered, inputs or outputs of risk management and product realization processes.
Records of changes, their review and any necessary actions shall be maintained (see 4.2.5).
7.3.10 Design and development files
The organization shall maintain a design and development file for each medical device type or medical device family. This file shall include or reference records generated to demonstrate conformity to the requirements for design and development and records for design and development changes.

## Sheet4
CANCER SCREENING CAMERA
Design & Development (Project Plan) -
|  |  |  | ARTICLES | PDF
DOCUMENT
|  |  |  | PROJECT EVALUATION FORM | TABLE1
|  |  |  | FEASIBILITY REPORT (Introduction/Team/On Manufacturability of Hardware/On Manufacturability of Software/Testing/Viability Study) | DOCUMENT
|  |  |  | PHASE REVIEW SHEET | TABLE2 |  | 7.3 Design and development
7.3.1 General
|  |  |  | OBJECTIVES OF PROJECT | DOCUMENT |  | The organization shall document procedures for design and development.
|  |  |  | Product Overview |  |  | 7.3.2 Design and development planning
|  |  |  | Hardware |  |  | The organization shall plan and control the design and development of product. As appropriate, design and development planning documents shall be maintained and updated as the design and development progresses.
|  |  |  | Firmware |  |  | During design and development planning, the organization shall document:
|  |  |  | Physical Req |  |  | a) the design and development stages; | Y
|  |  |  | Packing Req |  |  | b) the review(s) needed at each design and development stage; | Y
|  |  |  | Application Req |  |  | c) the verification, validation, and design transfer activities that are appropriate at each design and development stage; | Y
|  |  |  | Platform Req |  |  | d) the responsibilities and authorities for design and development; | Y
|  |  |  | Functional Req |  |  | e) the methods to ensure traceability of design and development outputs to design and development inputs; | Y
|  |  |  | Regulatory Req |  |  | f) the resources needed, including necessary competence of personnel. | Y
|  |  |  | Software Req |  |  | 7.3.3 Design and development inputs
[7 empty] | Inputs relating to product requirements shall be determined and records maintained (see 4.2.5). These inputs shall include: | Y | DESIGN INPUTS
[7 empty] | a) functional, performance, usability and safety requirements, according to the intended use; |  | a) functional, performance b) usability c) Safety requirements d) Regulatory e) output(s) of risk management f) information derived from previous similar designs; g) other requirements
b) applicable regulatory requirements and standards;
c) applicable output(s) of risk management;
d) as appropriate, information derived from previous similar designs;
e) other requirements essential for design and development of the product and processes.
These inputs shall be reviewed for adequacy and approved.
Requirements shall be complete, unambiguous, able to be verified or validated, and not in conflict with each other.
NOTE Further information can be found in IEC 62366–1.
7.3.4 Design and development outputs
Design and development outputs shall:
a) meet the input requirements for design and development;
b) provide appropriate information for purchasing, production and service provision;
c) contain or reference product acceptance criteria;
d) specify the characteristics of the product that are essential for its safe and proper use.
The outputs of design and development shall be in a form suitable for verification against the design and development inputs and shall be approved prior to release.
Records of the design and development outputs shall be maintained (see 4.2.5).
7.3.5 Design and development review
At suitable stages, systematic reviews of design and development shall be performed in accordance with planned and documented arrangements to:
REVIEW AND FINALIZED USER NEEDS | [6 empty] | a) evaluate the ability of the results of design and development to meet requirements;
b) identify and propose necessary actions.
Participants in such reviews shall include representatives of functions concerned with the design and development stage being reviewed, as well as other specialist personnel.
Records of the results of the reviews and any necessary actions shall be maintained and include the identification of the design under review, the participants involved and the date of the review (see 4.2.5).
7.3.6 Design and development verification
Design and development verification shall be performed in accordance with planned and documented arrangements to ensure that the design and development outputs have met the design and development input requirements.
The organization shall document verification plans that include methods, acceptance criteria and, as appropriate, statistical techniques with rationale for sample size.
[7 empty] | If the intended use requires that the medical device be connected to, or have an interface with, other medical device(s), verification shall include confirmation that the design outputs meet design inputs when so connected or interfaced. | CONNECTED DEVICES
Records of the results and conclusions of the verification and necessary actions shall be maintained (see 4.2.4 and 4.2.5).
7.3.7 Design and development validation
[7 empty] | Design and development validation shall be performed in accordance with planned and documented arrangements to ensure that the resulting product is capable of meeting the requirements for the specified application or intended use. | VALIDATION PLAN
The organization shall document validation plans that include methods, acceptance criteria and, as appropriate, statistical techniques with rationale for sample size.
Design validation shall be conducted on representative product. Representative product includes initial production units, batches or their equivalents. The rationale for the choice of product used for validation shall be recorded (see 4.2.5).
[7 empty] | As part of design and development validation, the organization shall perform clinical evaluations or performance evaluations of the medical device in accordance with applicable regulatory requirements. A medical device used for clinical evaluation or performance evaluation is not considered to be released for use to the customer. | perform clinical evaluations or performance evaluations of the medical device
[7 empty] | If the intended use requires that the medical device be connected to, or have an interface with, other medical device(s), validation shall include confirmation that the requirements for the specified application or intended use have been met when so connected or interfaced. | CONNECTED DEVICES
Validation shall be completed prior to release for use of the product to the customer.
Records of the results and conclusion of validation and necessary actions shall be maintained (see 4.2.4 and 4.2.5).
7.3.8 Design and development transfer
[7 empty] | The organization shall document procedures for transfer of design and development outputs to manufacturing. These procedures shall ensure that design and development outputs are verified as suitable for manufacturing before becoming final production specifications and that production capability can meet product requirements. | design and development outputs are verified as suitable for manufacturing
Results and conclusions of the transfer shall be recorded (see 4.2.5).
7.3.9 Control of design and development changes
The organization shall document procedures to control design and development changes. The organization shall determine the significance of the change to function, performance, usability, safety and applicable regulatory requirements for the medical device and its intended use.
[7 empty] | Design and development changes shall be identified. Before implementation, the changes shall be: a) reviewed; | a) reviewed; b) verified; c) validated, as appropriate; d) approved.
b) verified;
c) validated, as appropriate;
d) approved.
The review of design and development changes shall include evaluation of the effect of the changes on constituent parts and product in process or already delivered, inputs or outputs of risk management and product realization processes.
Records of changes, their review and any necessary actions shall be maintained (see 4.2.5).
7.3.10 Design and development files
[7 empty] | The organization shall maintain a design and development file for each medical device type or medical device family. This file shall include or reference records generated to demonstrate conformity to the requirements for design and development and records for design and development changes. | DESIGN HISTORY FILE
DESIGN AND DEVELOPMENT RESPONSIBILITY AND AUTHORITY
DESIGN AND DEVELOPMENT TRACABILITY MATRIX
REGULATORY PLAN/ LEGAL
RISK MANAGEMENT PLAN
DESIGN INPUTS
RISK MANAGEMENT FILE
PROPOSED SUPPLIERS
DESIGN OUTPUT
DESIGN OUTPUT FOR SOFTWARE
DESIGN VERIFICATION - HARDWARE
DESIGN VERIFICATION - SOFTWARE
DESIGN VALIDATION
DESIGN TRANSFER
BILL OF MATERIALS |  |  | DRAWINGS OF EACH PART - 25 DRAWIGS
Level | 1 | 2
Mechanical/Electrical | Mechanical | Mechanical
Category | Assembly | Injection moulding
Item | 637 | 637
part no. | 500-05002-01-00 | .71-05001-01-00
Description | Front Cover Assembly, aiTab | Front Cover, aiTab
Revision | 1 | 1
Qty | 1 | 1
Item Type | Make | Buy
Manufacturer/Supplier | CM | Imaginarium/Lonni
Manufacturer/Supplier Part Number | As per Drawing/Specification/Procedure given by NSV | As per Drawing/Specification given by NSV

## FINAL13JUNE
|  | Task | Duration | Start Date | End Date | Responsible Person R1 | Responsible Person R2 | Responsible Person R3 | Evidence
CONCEPT |  | Research
Development
Conceptualization
Feasibility
PLANNING |  | Task | Duration | Start Date | End Date | Responsible Person R1 | Responsible Person R2 | Responsible Person R3
| 1 | Quality Objectives
|  | Objective | Target Date | Resource Requirement | Reviewed BY | Approved By
| 2 | Product Description
|  | Name of the Product | Product Description | Trade Name | FDA Classification Name | Indian MDR Name
| 3 | Product Requirements
|  | Requirement ID | Requirement | Description
Functional Requirements
User Interface
Alarms and Alerts
Performance Requirements
Accuracy and Precision
Battery Life
Safety Requirements
Materials
Electrical Safety
Regulatory Requirements
Documentation
Usability Requirements
Ease of Use
Training
Support
| 4 | Design and Development Plan
Medical Device
Accessories
| 4a | D&D Stages
|  | Stage | Name of Responsible Person | Responsibility and Authority | Educational Quaifications | Experience with current organisation
| 4c | Competency Matrix
|  | Name of Person | Education | Training | Skiil | Experience
| 5 | Project Quality Plan
|  | Section | Description | Responsibility | Timeline | Acceptance Criteria
Design Control
|  | Design Input | Define user needs and regulatory requirements | Design Team | Month 1 | Requirements document reviewed and approved
|  | Design Output | Develop detailed design specifications | Engineering Team | Month 2 | Design output matches design input requirements
|  | Design Verification | Verify that design outputs meet design inputs | QA Team | Month 3 | Verification protocols executed and results documented
|  | Design Validation | Validate that the final product meets user needs and intended uses | Validation Team | Month 4 | Validation reports reviewed and approved
|  | Design Review | Conduct formal design reviews at key stages | Project Manager | Ongoing | Review meeting minutes and action items documented
Risk Management
|  | Risk Analysis | Perform risk analysis according to ISO 14971 | Risk Management Team | Month 1 | Risk analysis report completed and approved
|  | Risk Mitigation | Implement and document risk control measures | Engineering Team | Ongoing | Risk control measures verified and validated
|  | Risk Review | Review risk management file and update as necessary | QA Team | Ongoing | Risk management file reviewed and updated
Design Transfer
|  | Manufacturing Transfer | Transfer design to manufacturing | Manufacturing Team | Month 5 | Manufacturing processes validated and documented
|  | Training | Train manufacturing staff on new processes | Training Coordinator | Month 5 | Training records and competency assessments completed
Process Control
|  | Process Validation | Validate manufacturing processes | Validation Team | Month 6 | Process validation protocols executed and results documented
|  | In-Process Inspection | Define in-process inspection criteria and methods | QA Team | Ongoing | Inspection criteria met for all production batches
Product Control
|  | Incoming Inspection | Inspect incoming materials and components | QA Team | Ongoing | Incoming inspection records and non-conformance reports
|  | Final Product Testing | Perform final testing on finished products | QA Team | Ongoing | Final product testing records and non-conformance reports
Regulatory Compliance
|  | Regulatory Submission | Prepare and submit regulatory documentation (e.g., FDA 510(k), CE marking) | Regulatory Affairs Team | Month 7 | Regulatory submission acceptance
|  | Regulatory Updates | Maintain and update regulatory documentation | Regulatory Affairs Team | Ongoing | Regulatory files updated and maintained
Documentation Control
|  | Document Control | Implement document control procedures | Document Control Team | Ongoing | Controlled document system in place and maintained
Training and Competency
|  | Staff Training | Provide ongoing training for all relevant staff | HR and Training Team | Ongoing | Training records and competency assessments
Supplier Management
|  | Supplier Qualification | Qualify and audit suppliers | Supplier Quality Team | Ongoing | Approved supplier list and audit reports
Customer Feedback
|  | Post-Market Surveillance | Collect and analyze customer feedback and field performance data | Post-Market Surveillance | Ongoing | Customer feedback reports and action plans
Continuous Improvement
|  | Quality Audits | Conduct internal quality audits | Internal Audit Team | Biannually | Audit reports and corrective action plans
|  | CAPA | Implement corrective and preventive actions | QA Team | Ongoing | CAPA records and effectiveness checks
| 6 | Regulatory Plan
|  | Section | Description | Responsibility | Timeline | Acceptance Criteria
Regulatory Strategy
|  | Regulatory Classification and standards | Determine the regulatory classification of the device | Regulatory Affairs Team | Month 1 | Classification documented and reviewed
|  | Regulatory Pathway | Define the regulatory pathway (e.g., 510(k), PMA, CE marking) | Regulatory Affairs Team | Month 1 | Regulatory pathway approved by management
Pre-Submission Activities
|  | Pre-Submission Meeting | Schedule and conduct pre-submission meeting with regulatory bodies | Regulatory Affairs Team | Month 2 | Meeting minutes and action items documented
|  | Literature Review | Conduct literature review to support regulatory submission | Regulatory Affairs Team | Month 2 | Literature review report completed and reviewed
Design and Development
|  | Design Documentation | Prepare and maintain design history file (DHF) | Design Team | Ongoing | DHF reviewed and approved
|  | Risk Management | Develop risk management file (RMF) in compliance with ISO 14971 | Risk Management Team | Ongoing | RMF reviewed and approved
Clinical Evaluation
|  | Clinical Evaluation Plan | Develop clinical evaluation plan (CEP) | Clinical Affairs Team | Month 3 | CEP reviewed and approved
|  | Clinical Studies | Conduct necessary clinical studies | Clinical Affairs Team | Month 6 - Month 12 | Clinical study reports completed and reviewed
Regulatory Submission
|  | Technical Documentation | Prepare technical documentation for CE marking | Regulatory Affairs Team | Month 4 - Month 6 | Technical documentation reviewed and approved
|  | 510(k) Submission | Prepare and submit 510(k) premarket notification to FDA | Regulatory Affairs Team | Month 5 | 510(k) submission acceptance by FDA
|  | PMA Submission | Prepare and submit PMA application if applicable | Regulatory Affairs Team | As needed | PMA submission acceptance by FDA
|  | CE Marking | Submit technical documentation to notified body for CE marking | Regulatory Affairs Team | Month 6 | CE marking approval by notified body
Post-Submission Activities
|  | Regulatory Response | Respond to regulatory agency queries and deficiencies | Regulatory Affairs Team | As needed | Responses submitted within specified timelines
|  | Approval Monitoring | Monitor progress of regulatory submissions | Regulatory Affairs Team | Ongoing | Regular updates on submission status
Post-Market Activities
|  | Post-Market Surveillance | Develop and implement post-market surveillance plan (PMSP) | Post-Market Surveillance Team | Month 7 | PMSP reviewed and approved
|  | Adverse Event Reporting | Establish process for reporting adverse events | Regulatory Affairs Team | Ongoing | Adverse event reports submitted within required timelines
Regulatory Compliance
|  | Compliance Audits | Conduct internal audits to ensure ongoing regulatory compliance | Internal Audit Team | Annually | Audit reports and corrective actions documented
|  | Regulatory Updates | Monitor and implement changes in regulatory requirements | Regulatory Affairs Team | Ongoing | Regulatory files updated and maintained
Training and Education
|  | Staff Training | Provide training on regulatory requirements and updates | Training Coordinator | Ongoing | Training records and competency assessments
Continuous Improvement
|  | CAPA Management | Implement corrective and preventive actions for regulatory compliance issues | QA Team | Ongoing | CAPA records and effectiveness checks
| 7 | Risk Management Plan
|  | Section | Description | Responsibility | Timeline | Acceptance Criteria
Risk Management Planning
|  | Risk Management Plan | Develop a risk management plan in compliance with ISO 14971 | Risk Management Team | Month 1 | Plan reviewed and approved
|  | Risk Management Policy | Define the risk management policy | Senior Management | Month 1 | Policy documented and communicated
Risk Analysis
|  | Hazard Identification | Identify potential hazards associated with the device | Risk Management Team | Month 2 | Hazard analysis report completed and reviewed
|  | Risk Register | Create and maintain a risk register | Risk Management Team | Ongoing | Risk register updated with identified risks
|  | Failure Modes and Effects Analysis (FMEA) | Perform FMEA to identify and evaluate risks | Engineering Team | Month 3 | FMEA report completed and reviewed
Risk Evaluation
|  | Risk Assessment Criteria | Define criteria for risk acceptability | Risk Management Team | Month 2 | Criteria reviewed and approved
|  | Risk Ranking | Rank identified risks based on severity and probability | Risk Management Team | Month 3 | Risk ranking documented and reviewed
|  | Risk Acceptance | Determine which risks are acceptable based on predefined criteria | Risk Management Team | Month 3 | Risk acceptance decisions documented
Risk Control
|  | Risk Mitigation | Develop and implement risk control measures | Engineering Team | Month 4 | Risk control measures documented and implemented
|  | Verification of Risk Controls | Verify effectiveness of risk control measures | QA Team | Month 5 | Verification reports completed and reviewed
|  | Residual Risk Evaluation | Evaluate residual risks after implementation of controls | Risk Management Team | Month 5 | Residual risk documented and reviewed
Risk Management Review
|  | Risk Management Review | Conduct regular reviews of the risk management process | Risk Management Team | Quarterly | Review meeting minutes and action items documented
Production and Post-Production Activities
|  | Production Risk Management | Identify and manage risks during production | Manufacturing Team | Ongoing | Production risk management plan reviewed and approved
|  | Post-Market Surveillance | Collect and analyze post-market data to identify new risks | Post-Market Surveillance Team | Ongoing | Post-market surveillance reports and action plans
Documentation and Communication
|  | Risk Management File | Maintain a comprehensive risk management file | Document Control Team | Ongoing | Risk management file updated and maintained
|  | Risk Communication | Communicate risk management activities and outcomes to stakeholders | Risk Management Team | Ongoing | Communication records and stakeholder feedback
Training and Competency
|  | Staff Training | Provide training on risk management processes and procedures | Training Coordinator | Ongoing | Training records and competency assessments
Continuous Improvement
|  | CAPA Management | Implement corrective and preventive actions for identified risks | QA Team | Ongoing | CAPA records and effectiveness checks
|  | Risk Management Audit | Conduct internal audits of the risk management process | Internal Audit Team | Annually | Audit reports and corrective action plans
This quality plan ensures that all aspects of risk
DESIGN INPUT PHASE | 8 | DI Listing per intended Use
|  | User Needs ID No. | Description | FINALISE IT | User Needs ID No. | Description
Product Specification as per Design Team
| 9 | Specification No | Details | FINALISE IT | Specification No | Details
|  |  | Functional |  |  | Functional
|  |  | Technical |  |  | Technical
|  |  | Features |  |  | Features
|  |  | Regulatory |  |  | Regulatory
Mechanical
Electronics
Software
| 10 | Applicable Regulatory Req & Standards
|  | Standard | Title | Scope | Reason for Adoption | Approvved By
Legal Law of the Country
BIS
ISO
IEC
Inhouse Specification
| 11 | Risk Analysis and its Output
|  | Document Name | Date of Finalisation
| 12 | Proposed Suppliers
|  | Name | Contact Person | Material | Specifications | Acceptance Criteria
13
DESIGN OUTPUT PHASE | START WITH INPUTS FROM STEP 9 | List Design Output- Mechanical | Finalize Design Output- Mechanical |  | INPUT |  |  | OUTPUT
|  | List Design Output - Electronics | Finalize Design Output- Electronics |  | Product Specification as per Design Team |  |  | Product Specification as per Design Team
|  | List Design Output-Software | Finalize Design Output- Software |  | Specification No | DESCRIPTION | ACCEPTANCE CRITERIA | Specification No | DESCRIPTION | ATTACH EVIDENCE OF OUTPUT
|  | Define the Mechanical Product BOM | Finalize the Mechanical Product BOM
|  | Define the Electronic Product BOM | Finalize the Electronic Product BOM
|  | Define the Proposed suppliers | Suppliers List Final
|  | Mechanical drawing | Finalize the Mechanical drawings
|  | Work Instructions | Finalize the Work Instructions
|  | Specification | Finalize Specifications
|  | Electronics Drawings | Finalize the Electronics Drawings
Product and Process Risk Assessment
|  | Product Review- Hardware | Final Product Review- Hardware
|  | Product Review-Software | Final Product Review-Software
Verification Plan
Verification Plan
|  | Document Name | Date of Finalisation
Design Verification Phase | 14 | Design Verification report
|  | INPUT |  |  | OUTPUT
|  | Product Specification as per Design Team |  |  | Product Specification as per Design Team
|  | Specification No | DESCRIPTION | ACCEPTANCE CRITERIA | Specification No | DESCRIPTION | ATTACH EVIDENCE OF OUTPUT | ATTACH EVIDENCE OF VERIFICATION | VERIFIED BY | RESULT | APPROVED BY
Design Validation Phase | 15 | Design Validation report
|  | INPUT |  |  | OUTPUT
|  | Product Specification as per Design Team |  |  | Product Specification as per Design Team
|  | Specification No | DESCRIPTION | ACCEPTANCE CRITERIA | Specification No | DESCRIPTION | ATTACH EVIDENCE OF VALIDATION |  | VERIFIED BY | RESULT | APPROVED BY
Design Transfer Phase | 16 | Design Transfer report
BOM
Drawings
SOPs & WI
Test Procedure
Labelling
Packaging
Electronics Data
Software
RISK
Risk ID | Phase/Process | Hazard | Harm | Probability | Sererity | Any Legal Requirement | RPN Number | Existing Implementation | Further action required (y/n) | Design ID for implementation | Acceptance Criteria | To be verified by | Verified BY | Verified on Date | Approved /Rejected | Evidence

## Sheet6
Section | Description | Responsible Party | Timeline | Acceptance Criteria
Risk Management Planning
Risk Management Plan | Develop a risk management plan in compliance with ISO 14971 | Risk Management Team | Month 1 | Plan reviewed and approved
Risk Management Policy | Define the risk management policy | Senior Management | Month 1 | Policy documented and communicated
Risk Analysis
Hazard Identification | Identify potential hazards associated with the device | Risk Management Team | Month 2 | Hazard analysis report completed and reviewed
Risk Register | Create and maintain a risk register | Risk Management Team | Ongoing | Risk register updated with identified risks
Failure Modes and Effects Analysis (FMEA) | Perform FMEA to identify and evaluate risks | Engineering Team | Month 3 | FMEA report completed and reviewed
Risk Evaluation
Risk Assessment Criteria | Define criteria for risk acceptability | Risk Management Team | Month 2 | Criteria reviewed and approved
Risk Ranking | Rank identified risks based on severity and probability | Risk Management Team | Month 3 | Risk ranking documented and reviewed
Risk Acceptance | Determine which risks are acceptable based on predefined criteria | Risk Management Team | Month 3 | Risk acceptance decisions documented
Risk Control
Risk Mitigation | Develop and implement risk control measures | Engineering Team | Month 4 | Risk control measures documented and implemented
Verification of Risk Controls | Verify effectiveness of risk control measures | QA Team | Month 5 | Verification reports completed and reviewed
Residual Risk Evaluation | Evaluate residual risks after implementation of controls | Risk Management Team | Month 5 | Residual risk documented and reviewed
Risk Management Review
Risk Management Review | Conduct regular reviews of the risk management process | Risk Management Team | Quarterly | Review meeting minutes and action items documented
Production and Post-Production Activities
Production Risk Management | Identify and manage risks during production | Manufacturing Team | Ongoing | Production risk management plan reviewed and approved
Post-Market Surveillance | Collect and analyze post-market data to identify new risks | Post-Market Surveillance Team | Ongoing | Post-market surveillance reports and action plans
Documentation and Communication
Risk Management File | Maintain a comprehensive risk management file | Document Control Team | Ongoing | Risk management file updated and maintained
Risk Communication | Communicate risk management activities and outcomes to stakeholders | Risk Management Team | Ongoing | Communication records and stakeholder feedback
Training and Competency
Staff Training | Provide training on risk management processes and procedures | Training Coordinator | Ongoing | Training records and competency assessments
Continuous Improvement
CAPA Management | Implement corrective and preventive actions for identified risks | QA Team | Ongoing | CAPA records and effectiveness checks
Risk Management Audit | Conduct internal audits of the risk management process | Internal Audit Team | Annually | Audit reports and corrective action plans
This quality plan ensures that all aspects of risk
This quality plan covers various aspects of the product lifecycle, from design and develo

## Sheet7
Section | Description
Design and Development Planning
Design and Development Plan | Develop a comprehensive plan including objectives, timelines, and responsibilities
Design Input
User Needs and Requirements | Collect and document user needs and regulatory requirements
Risk Management Planning | Develop a risk management plan according to ISO 14971
Design Output
Preliminary Design | Create initial design concepts and prototypes
Detailed Design | Develop detailed design specifications and drawings
Design Review | Conduct formal design reviews at key stages
Design Verification
Verification Activities | Perform tests and analyses to verify design outputs meet inputs
Design Validation
Validation Planning | Develop a plan for design validation
Validation Activities | Conduct validation tests to ensure device meets user needs
Clinical Evaluation | Perform clinical studies if necessary
Design Transfer
Transfer to Manufacturing | Transfer design specifications to manufacturing
Process Validation | Validate manufacturing processes to ensure consistency
Production
Pilot Production | Conduct pilot production to test manufacturing processes
Full-Scale Production | Begin full-scale production
Regulatory Compliance
Regulatory Submission | Prepare and submit regulatory documentation (e.g., FDA 510(k), CE marking)
Regulatory Approval | Obtain necessary regulatory approvals
Post-Market Surveillance
Post-Market Surveillance Plan | Develop and implement a post-market surveillance plan
Adverse Event Reporting | Establish a process for reporting adverse events
Continuous Improvement
CAPA Management | Implement corrective and preventive actions based on post-market data
Quality Audits | Conduct internal audits to ensure compliance with ISO 13485
Training and Competency
Staff Training | Provide ongoing training on design control and regulatory requirements
Documentation Control
Document Control | Implement document control procedures to maintain design and development records