| Day(s) | Goal in simple words | What you tell the team (business language) | What the team actually does (tech language) | Example |
| --- | --- | --- | --- | --- |
| 1–2 | Freeze demo story | “In the exhibition, I want to show 2–3 stories: how a customer order becomes a finished device, how we track quality issues, and how we show DHR/traceability for audits.” | Run a short workshop, define user personas (Sales, Production, QA), document 2–3 user journeys and list only the required screens and fields. Create a simple spec/Confluence page. technologyrivers+1​ | Story 1: Customer orders 1000 syringes → Sales order → Production order → QC passed → DHR view for that lot. Story 2: In-process rejection → NC → CAPA → updated inspection plan.expandable+1​ |
| 1–2 | Define modules in scope | “For this prototype, I only need: Masters (Customer, Item, BOM), Production (Work Orders), Quality (Inspection, NC/CAPA), and DHR/Traceability screen. Nothing else for now.” | Create a high-level module list and mark “In scope now” vs “Later”. Prepare a one-page module map diagram. erpresearch+1​ | Example module map: 1) Sales & Customer, 2) Item & BOM, 3) Production, 4) Quality/NC/CAPA, 5) DHR & Traceability. Show this as a box diagram in slides. |
| 1–3 | Agree tech stack & environment | “Use whatever stack you are comfortable with, but I need a web app that runs in browser and can be hosted on cloud, with 3–4 demo logins.” | Choose front-end (e.g., React), back-end (e.g., Node.js or .NET), DB (PostgreSQL/MySQL) and cloud (AWS/Azure). Create base project, repo, environments (dev/demo). digiteum+1​ | Example sentence: “I don’t care if it is React or Angular; I care that it opens reliably in Chrome during the exhibition and doesn’t crash.” |
| 2–4 | Draw and agree screens (wireframes) | “Before coding, I want to see sketches of the main screens: Dashboard, Customer, Item/BOM, Work Order, QC/Inspection, NC/CAPA, DHR.” | UX person makes wireframes in Figma or similar. Devs review for feasibility. Finalize layout: left menu, list view, detail view. shivlab+1​ | Example: Show them a very simple ERP screenshot from web and say: “Something like this: left menu with ‘Sales / Production / Quality / DHR’ and table in the middle.” |
| 3–4 | Define data fields (business view) | “For each screen, let us list only the essential fields that a medical device company expects to see.” | Create field lists per entity: Customer (Name, Country, Type), Item (Code, UDI, Revision, Class), BOM (Parent Item, Component, Qty), Work Order, Inspection, NC, CAPA, DHR. expandable+2​ | Example for Item: “Item Code, Description, UDI, Revision, Device Class, Sterile/Non-Sterile, Critical Item Yes/No.” For DHR: “Item, Lot No, Work Order, QC results, NCs, Approvals.” |
| 3–6 | Build front-end skeleton | “By Day 6, I want to be able to click around: menus should open, screens should change, even if data is fake.” | Implement routing and static pages for all key screens according to wireframes. Use mock data or placeholders. Setup basic theme and logo placeholder. shivlab+1​ | Example: You click “Production → Work Orders” and see a table with a few hard-coded rows; click any row to open a detail page. |
| 4–7 | Design minimal database & APIs | “Make sure whatever we build now can save real dummy data: some customers, some items, a few work orders and quality records.” | Design DB schema for Users/Roles, Customers, Items, BOM, Sales Orders, Work Orders, Inspection, NC/CAPA, DHR. Create basic CRUD APIs for these tables. erpsoftwareblog+2​ | Example: Ask them, “Show me the ER diagram of tables you will create for Item, BOM, Work Order, QC, DHR. I need to see how traceability will work.” |
| 6–8 | Seed realistic demo data | “Fill the system with believable example data for 2–3 types of devices, with orders and some quality events, so the story looks real.” | Write DB seed scripts to insert demo customers, items, BOMs, sample orders, WIP jobs, passed/failed inspections, NCs, CAPAs. erpfocus+2​ | Example: Device A – “Sterile Disposable Syringe 5 ml”; Device B – “Cardiac Stent”; each with its own BOM. Create one order where everything passes, and one where an NC is raised. |
| 7–10 | Connect UI to backend | “Now I want the screens to work with actual data: when I click Save, it should store in the database and show up in the list.” | Replace mock data with live API calls. Implement create/edit forms and list pages for Customer, Item, BOM, Work Order, Inspection, NC. Handle simple validation and error messages. digiteum+1​ | Example: You create a new Customer “ABC MedTech Pvt Ltd”; after saving, it appears instantly in the Customer list and can be used in a Sales Order. |
| 8–11 | Build DHR & traceability view | “I want one hero screen: I enter Item + Lot/Batch and see everything linked to it – order, work order, QC, NC, approvals – like a simple DHR.” | Implement a DHR summary page that joins tables and displays all related records for a selected batch/lot. Add filters (Item, Lot, Date). expandable+2​ | Example: Type “Lot 2301-A” → see: Sales Order #1005, Work Order #WO-45, QC result PASS, one NC closed, Released by QA with date and name. |
| 9–12 | Add regulatory flavour & polish | “Screens must look like they understand ISO 13485 / FDA: show revision, created/approved dates, who did what, and status.” | Add fields/labels for revision, created/modified by, timestamps, status badges. Add simple role-based visibility if possible. Apply consistent styling, icons, spacing. expandable+2​ | Example text on screen: “Approved by: QA Manager (R. Sharma) on 01-Feb-2026”; status tags: “Open / In Progress / Closed / Released”. |
| 10–13 | Host demo on cloud | “For the exhibition, I need a stable URL and a few demo users so I can show from any laptop.” | Deploy prototype to chosen cloud provider. Configure demo database. Create demo users (Admin, Sales, Production, QA). Setup simple monitoring/logging. oracle+1​ | Example logins: qa_demo / prod_demo / sales_demo (all with simple passwords for internal use). |
| 11–13 | Create demo reset mechanism | “After many demos, data will get messy. I want a one-click way to reset demo data overnight.” | Implement a script or admin endpoint that clears transactional data and re-runs the seed scripts. Optionally schedule a daily reset. erpfocus+1​ | Example: Button or script called “Reset_demo_ERP” that restores the system to initial sample companies, orders, and QC records. |
| 12–14 | Prepare demo script | “Write down, step by step, what I should click and what I should say on each screen, for a 7–10 minute demo.” | Translate user journeys into a script with numbered steps, screenshots, and talking points; store in a shared doc. technologyrivers+2​ | Example: Step 1 – open Dashboard; Step 2 – open Sales Order SO-1005; Step 3 – open linked Work Order; Step 4 – show QC results; Step 5 – show DHR screen and summarise benefits. |
| 13–15 | Create slides & recording | “Please give me: 4–6 slides explaining the product, plus a short screen-recorded video as backup for the booth.” | Capture screenshots, design a short deck (Problem → Solution → Key Flows → Roadmap), and record a 2–3 minute screen-capture walkthrough with voice-over. userflow+2​ | Example slide titles: “Why a dedicated ERP for Medical Devices?”, “From Order to DHR in 5 clicks”, “Quality & Compliance (NC/CAPA, Traceability)”, “Our Roadmap”. |
| 14–15 | Internal rehearsal & feedback | “Let us do 3–4 mock demos internally and fix any slow screens or confusing steps before the exhibition.” | Run test demos, note performance issues and UX confusion, fix critical bugs, fine-tune data and script. technologyrivers+2​ | Example: Ask them, “Assume you are a QA Manager visiting the booth – does this DHR screen answer your audit questions in 1 minute?” Adjust based on their feedback. |

- only objective is a smooth, believable demo of 2–3 flows by Day 15, not a full ERP.